## MFE Tracker
INSERT LOGO
ACTION TRACKING REGISTER
MFE TRACKER
Date Raised | Originator (Source) | Findings | Recommended Action | Status | Action Party | Action Taken | Evidence | Reference No
24th FEB. 2026 | AHIA WELL 09 | Office caravans structurally defective | Conduct a comprehensive structural integrity assessment of all office and accommodation caravans and implement a phased replacement or refurbishment programme based on risk priority | CLOSED | MTC/RIG MANAGER | Discussed in operation meeting and it was closed out. | Image | PH/MFI/AHIA/02/26
|  | Concern over Ego point personnel convertion | Management should review the employment conversion process and communicate a clear roadmap to affected personnel to sustain morale, competence retention and operational continuity. | CLOSED | HR MANAGER | Discussed in operation meeting and it was closed out. | Documented | PH/MFI/AHIA/02/26
|  | Hotel experiencing inadequate power | Assess the adequacy of the existing power supply to the accommodation facility and provide additional generating capacity where necessary to ensure uninterrupted welfare services | OPEN | MTC/RIG MANAGER | Discussed in operation meeting. There is great improvement but not perfect yet | Image | PH/MFI/AHIA/02/26
|  | No visible MSDS at chemical storage. | Ensure current Material Safety Data Sheets (MSDS/SDS) are readily accessible at all chemical storage Ensure current Material Safety Data Sheets (MSDS/SDS) are readily accessible at all chemical storage | CLOSED | RIG MANAGER | A stand was constructed by the welders and MSDS is properly dispalyed at the chemical storage zone | Image | PH/MFI/AHIA/02/26
|  | No hotel crash bags | Provide strategically located emergency crash bags within the accommodation area to improve medical emergency response capability and personnel protection. | CLOSED | HSE MANAGER | Request and made it was procurred | Image | PH/MFI/AHIA/02/26
|  | Poor Drug and Alcohol documentation | Strengthen the Drug and Alcohol Management Programme by ensuring all testing activities are adequately documented, traceable and fully compliant with Renaissance and TECON requirements. | CLOSED | HSE MANAGER | It was reported and policies were sent and adequately pasted in strategic places. | Image | PH/MFI/AHIA/02/26
|  | No sandbags at Safe Haven | Expedite the procurement and installation of protective sandbags at the designated Safe Haven in accordance with the facility securityrisk assessment and emergency preparedness requirements. | CLOSED | TECON/ CLIENT MGT | It was raised as a concern during the operations meeting | Image | PH/MFI/AHIA/02/26
|  | No automated alarm/PA announcement system. Install automated emergency alarm and public address system. | Evaluate and implement an integrated emergency alarm and public address system to improve emergency communication, personnel accountability and response effectiveness during abnormal situations | CLOSED | TECON MANAGEMENT | Requisition was made and it has been closed out | Image | PH/MFI/AHIA/02/26
11th AUG 2025 | OBAGI WELL 80 | The flood light stand has no secondary retention on them. | Crew should install secondary retentions on all the Light Stand | CLOSED | TECON – Rig Electrician | Retentions have been placed on the stands | Image | PH/MFI/OBG/08/25
|  | Some site leadership team members were putting on worn out coveralls. | The GM Operations and the group HSE Manager should ensure provision of PPEs. | CLOSED | TECON MANAGEMENT | PPE was provided for all | PPE Issuance List | PH/MFI/OBG/08/25
|  | The drain pan for the Diesel Storage tank was open. | The drain pan should always remain closed | CLOSED | TECON -Rig Mechanic | Drain pans are shut at all times | n/a | PH/MFI/OBG/08/25
|  | Water leakage on the butterfly valve. | The butterfly valve on the water active tank 2 is to be replaced. | CLOSED | TECON – Pump Supv. | Valve procured and delivered | Material transfer Record | PH/MFI/OBG/08/25
|  | Some air hoses connections had no whip check on them. | Install whip-checks on all the hoses connections. | CLOSED | TECON – Field Engr. | all hoses with connections have whipschecks | Image | PH/MFI/OBG/08/25
|  | The fuel filter on the fire pump is old and needed to be replaced | Replace the old fuel filter with a new one. | CLOSED | TECON - Rig Mechanic. | New fuel filter installed | Image | PH/MFI/OBG/08/25
|  | The pressure gauge on the de-gasser was not functioning. | Replace the gauge with a functional gauge. | CLOSED | TECON – Field Engr. | Open |  | PH/MFI/OBG/08/25
|  | Electric sockets were buried in rain water. | All electric cables and sockets should be put inside cable trays. | CLOSED | TECON – Rig Electrician | Open |  | PH/MFI/OBG/08/25
27TH MAY 2025 | OGBELE WELL 9 | Backup Gen-set on location is defective. | To be fixed or replaced. | CLOSED | PROJECT MGR | The rig managent team were involved | Image | PH/MFE/OGB/08/2025
|  | DSV's Accommodation Air conditioner not fully functional | To be fixed or replaced. | CLOSED | PROJECT MGR | The rig managent team were involved |  | PH/MFE/OGB/08/2025
|  | No office for Third party service Supervisors | New offices should be provided | OPEN | PROJECT MGR | Called the attention of the management |  | PH/MFE/OGB/08/2025
|  | No gas testers on board | Gas testers should be provided urgently | CLOSED | HSE MANAGER | The HSE team attention were called | Documented | PH/MFE/OGB/08/2025
|  | No teatime beverages for client and HWO crew | Beverages for personnel should be provided | CLOSED | PROJECT MGR | The rig managent team were involved |  | PH/MFE/OGB/08/2025
|  | Ambulance has no Spare tyre, it has expired and other 4 tyres are worn out | Ambulance tires should be changed, and spares provided. | CLOSED | MTC MANAGER | The rig managent team were involved |  | PH/MFE/OGB/08/2025
|  | No vehicle for HWO Supervisor | Vehicles for supervisors should be provided | CLOSED | PROJECT MGR | The rig managent team were involved | picture | PH/MFE/OGB/08/2025
|  | Crane Exhaust defective | Preriodic maintenance and certification | CLOSED | MTC MANAGER | The rig managent team were involved |  | PH/MFE/OGB/08/2025
26TH SEPT. 2024 | OGBELE | the detroit rig 101 power generators are both bad | Develop a preventive maintence schedule and ensure compliance | CLOSED | PROJECT MGR | The rig managent team were involved | Documented | PH/MFI/OGB/09/2024
|  | Compressor essential and critical for running MCC is still bad | Develop a preventive maintence schedule and ensure compliance | CLOSED | PROJECT MGR | The rig managent team were involved | Documented | PH/MFI/OGB/09/2024
|  | Observed the 100 ton crane is faulty | Develop a preventive maintence schedule and ensure compliance | CLOSED | PROJECT MGR | The rig managent team were involved | Documented | PH/MFI/OGB/09/2024
|  | Observed the air condition in the MCC is faulty | Develop a preventive maintence schedule and ensure compliance | CLOSED | PROJECT MGR | The rig managent team were involved | Documented | PH/MFI/OGB/09/2024
4TH MAY 2023 | OMOFEJO | poor waste segregation | More waste bins are required | CLOSED | H/B MGT | Called the attention of the management | picture | PH/MFI/OMO/05/2023
|  | No micro wave in the kitchen | Micro wave should be provided in the kitchen and galley | CLOSED | H/B MGT | Called the attention of the management | picture | PH/MFI/OMO/05/2023
|  | House boat has only 3lifebuoys and without launching ropes | 12 yards marine ropes should be provided and attached to each of the lifebuoys | CLOSED | H/B MGT | Called the attention of the management | picture | PH/MFI/OMO/05/2023
|  | Leaking roof in the recreation | Repair on going as maintenance team were on board | CLOSED | H/B MGT | Called the attention of the management | picture | PH/MFI/OMO/05/2023
28TH SEPT. 2022 | GBARAN 16 | Observed the operational vehicles were due for maintenance | The developed preventive maintenance scheduled should be followed | CLOSED | SUPERVISOR | The responsible parties attention was called | Documented | PH/MFI/GBA/09/2022
|  | Observed drill pipes were layed on the flooded ground | All pipes should be properly racked on a rack | CLOSED | SUPERVISOR | All the pipes were racked on the rack and properly cover to avoid damage on the thread | Documented | PH/MFI/GBA/09/2022
|  | Observed poor hosekeeping at the deck area | Good housekeeping before and after each task | CLOSED | HSE/ PIC | Personnel were called for housekeeping and it was done | Documented | PH/MFI/GBA/09/2022
|  | Observed the forklift consumes much oil | Preventive management is required | CLOSED | MTC MGR | The action of the action party was called | Documented | PH/MFI/GBA/09/2022
|  | Observed the electric cables not properly arranaged | All electrici cable should be properly safety guarded | CLOSED | Hotel Magt | Called the attention of the management | Picture | PH/MFI/GBA/05/2022
10TH MAY 2022 | GBARAN 16 | Observed most fire extinguisher's were expired | Develop a tracker/ reminder to ensure a follow up | CLOSED | Hotel Magt | All fire extinguisher must be certified and fit for purpose | Documented | PH/MFI/GBA/05/2022
|  | Observed the lundry is not fit for purpose | The laundry room should be properly equipped and kept | CLOSED | Hotel Magt | personnel were encouraged to ensure proper housekeeping within the room | Picture | PH/MFI/GBA/05/2022
15th November, 2021 | AFREMO 6 | Storage of past handover notes were destroyed by the effect of submerged offices during JUB preloading | Notebooks as well as other handy documents should be returned to the base for safe keeping during demobilization. | CLOSED | Rig Team | Notebooks and other handy documents was kept well and returned to the base for safe keeping. | Documented | PH/MFI/AFR/11/2021
|  | Email handover notes are said to be sent, printed and documented at the worksite | Ensure both incoming and outgoing personnel sign off. | CLOSED | Rig Supervisor | Personnel duely sign in and sign out as required | Documented | PH/MFI/AFR/11/2021
|  | Only supervisors write their handover notes, other key personnel hand over verbally | Field Engineer, Jack Operators and Pump operators should also have written handover notes. Handover notes should be documented at the end of shift and end of tour. Supervisors to oversee handover of other roles. | CLOSED | Rig Supervisor | Ensure proper handover note was written with key personnel involved | Documented | PH/MFI/AFR/11/2021
|  | Cracks and other defects on joints and connections • Equipment lifespan reduction • Reduction in equipment strength • Reduce equipment value | Schedule regular equipment function test • Wash equipment • Grease equipment and connections regularly • Prime when corrosion effects are observed • Painting as per schedule or planned | CLOSED | Rig Supervisor | Protective linings or special coatings was used to prevent forward corrosion | Pictures | PH/MFI/AFR/11/2021
|  | Other causes of corrosion on equipment observed: • Reduced tubular OD and ID | Follow the corrosion control management plan as per company policy | CLOSED | Rig Team | Protective linings or special coatings was used to prevent forward corrosion | Pictures | PH/MFI/AFR/11/2021
|  | Environmental Salt Water | Regular corrosion control and proper storage | CLOSED | Rig Team | Protective linings or special coatings was used to prevent forward corrosion | Pictures | PH/MFI/AFR/11/2021
|  | 0.46psi/ft Brine, 0.51psi Brine in Annulus B casing affecting the workstring | Talk to SPDC REP to use corrosion inhibitors | CLOSED | Rig Supervisor | Corrosion inhibitors was used on pipes, Protective linings or special coatings was used to prevent forward corrosion in pipes | Pictures | PH/MFI/AFR/11/2021
JUNE 24TH 2021 | FORCADOS 73 | Annulus B casing affecting the | All personnel to be provided with complete PPEs needed for the operation | CLOSED | QHSE | PPE was provided for all | Issuance list | TNPH/MFI/forc/06/2021
|  | workstring | Replacement to be sent ASAP | CLOSED | TECON | Requsition was made and its replacement was procured | Requisition form | TNPH/MFI/forc/06/2021
|  | SPM 600 and mechanical pump Temp pre-mob expired | To follow up in getting stickers as soon as they are available | CLOSED | TECON | Pre-mob stickers were made available | Picture | TNPH/MFI/forc/06/2021
|  | Drill pipes have plenty scales due to rust | To be replaced with plastics- coated drill pipes | CLOSED | TECON | Replacement was made with coated plastics drill pipes | Pictures | TNPH/MFI/forc/06/2021
|  | Bad diesel supplied to the location and causing damages to ICEs | TECON management to engage SPDC on this reoccuring issue | CLOSED | TECON/SPDC | This was discussed in the management operations meeting |  | TNPH/MFI/forc/06/2021
Jan 21st 2020 | FORCADOS 51 | Gangway positioning between the SEWOP and platform 51 was badly positioned | Immediate correction | CLOSED | SUPERVISOR | This was corrected immediately | Picture | TNPH/MFI/forc/01/2021
|  | Slippery work deck | Personnel were asked to clean up the entire deck with rig-wash | CLOSED | QHSE | Housekeeping was encouraged at daily tool box talks | Tool box documentation | TNPH/MFI/forc/01/2021
|  | The terrifying situation and difficulty with logistics | Proper planning and timely preparation prior to operation | CLOSED | SUPERVISOR | This was discussed in the management operations meeting |  | TNPH/MFI/forc/01/2021
|  | The bad nature of the boat landing | The pad at extreme and its torn bottom to be worked on | CLOSED | SUPERVISOR | Proper maintenance prior to mobilization was encouraged | Maintenance form | TNPH/MFI/forc/01/2021
2019-01-01 | P $ A | Lack of absorbent sheet | Absorbent sheet should be made available at all times by setting a minimum reorder level. | CLOSED | QHSE/HWO | Requisition was made on | PICTURE | TNPH/MFI/P&A/01/19
|  | Ambulance was wrongly parked | The entrance should always be from obstructions. Security guards to enforce. | CLOSED | QHSE | The access control personnel were called to order to ensure proper parking of vehicles | PICTURE | TNPH/MFI/P&A/01/19
|  | Ambulance A/C not working | Fix Ambulance A/C | CLOSED | QHSE/MTC | Maintenance request form was filled | Maintenance form | TNPH/MFI/P&A/01/19
|  | Observed the HWU JJ Henry 340k Unit does not have a HAC diagram and a noise map. | A HAC diagram should be generated to educate crew on the hazardous arae of the operation | CLOSED | TECON | HAC Diagram and a noise map was developed | HAC Diagram | TNPH/MFI/P&A/01/19
|  | No adequate muster barge on location for POB to converge in case of emergency evacuation | TECON& NAOC team to discuss on getting a dedicated muster barge in location | CLOSED | TECON/NAOC | Requisition was made and a dedicated muster barge was provided | Job Completion form | TNPH/MFI/P&A/01/19
|  | No designated area for smoking | There should be a designated area for smoking | CLOSED | TECON/NAOC | Desigmated smooking area was mapped out | Picture | TNPH/MFI/P&A/01/19
|  | Some rooms has plumbering issues making the lavatories unusable | A routine check should be carried out on schedule | CLOSED | TECON/NAOC | Regular maintenace and request for maintenance form was made available | Job Completion form | TNPH/MFI/P&A/01/19
|  | poor check carried out by the access control team | Retrain Access control team. | CLOSED | TECON/NAOC | AWARENESS TRAINING CONDUCTED ON SITE | Attendance | TNPH/MFI/P&A/01/19
May.2. 2018 | MFI TECON | Slings are littered on the floor in the ware house | Sling racks should be constructed | CLOSED | MFS MGR | Requsistion was made | Job Completion form | TNPH/MFI/P&A/01/18
| MFI TCON | Gas cylinders are not secured | Ensure all Gas cylinders are properly secured vertically and chained | CLOSED | QHSE/HWO | Personnel were told to always secure the gas cylinders vertically and chained | Picture | TNPH/MFI/P&A/01/18
| MFI TCON | Waste bins are not properly arranged | Waste bins should be properly kept in upright position and organized | CLOSED | QHSE | Close montoring and training on how best to handle company's property | Attendance | TNPH/MFI/P&A/01/18
| MFI TCON | Fire extinguisher at the warehouse are not enough and no enough stand for it | Provide appropriate stand for extinguishers | CLOSED | QHSE | Requisition was made on fabricating of stands for all the fire extinguishers | Work order | TNPH/MFI/P&A/01/18
| MFI TCON | Diesel is stored in the warehouse close to a flammable material | Diesel to be stored in a proper facility outside the warehouse | CLOSED | HWO/MTCE | Diesel is stored in the warehouse was moved away from flammable material | PICTURES | TNPH/MFI/P&A/01/18
| MFI TCON | Emergency exit door is blocked with some casing tools | All emrgency exits to be free from obstructions | CLOSED | QHSE | The industrial fan obstructing easy access was moved out | PICTURES | TNPH/MFI/P&A/01/18
| MFI TECON | No well defined park for vehicles at the yard | provision of a well mapped out car park for vehicles | OPEN | QHSE |  |  | TNPH/MFI/P&A/01/18
| MFI TECON | No speed limit signages in the yard | provision of the speed limit signages should be carried out | OPEN | QHSE |  |  | TNPH/MFI/P&A/01/18
Aug.15.2017 | MFI TECON- PNA (HWO) | Poor housekeeping of Toilet and offices | Engage cleaners on the interim | CLOSED | HWO/MTCE |  | Available on site | TNPH/MFI/P&A/01/17
| MFI TECON -PNA (HWO) | Quarantined Waste bins without lids | Ship to Town | CLOSED | QHSE/LOG |  | all waste bins removed from site | TNPH/MFI/P&A/01/17
| MFI TECON -PNA (HWO) | Lack of absorbent sheets | Request from SPDC | CLOSED | HWO |  | absorbent sheets now available on site | TNPH/MFI/P&A/01/17
| MFI TECON- PNA (HWO) | HSE Statistics board very shabby and on the floor. | Request from SPDC | CLOSED | QHSE |  | standard statistics board on site | TNPH/MFI/P&A/01/17
| MFI TECON -PNA (HWO) | Backup Slings with Expired Certs | Backload immediately to town | CLOSED | HWO/LOG |  | see slings register on site | TNPH/MFI/P&A/01/17
| MFI TECON -PNA (HWO) | Electrical compressor down | Mechanic to fix ASAP | CLOSED | HWO/MTCE | Maintenance request form was filled | compressor repaired | TNPH/MFI/P&A/01/17
| MFI TECON- PNA (HWO) | Fumigation not carried out on OBGN-18 | Fumigation must be carried out prior to any rig move. | CLOSED | QHSE/HWO | Fumigation is done monthly on site and camp | available on site | TNPH/MFI/P&A/01/17
| MFI TECON -PNA (HWO) | Wind SURF is bad | Send the welders to repair | CLOSED | HWO/MFS |  | available on site | TNPH/MFI/P&A/01/17
| MFI TECON -PNA (HWO) | Fire pump [hydrant] is leaking from suction head. | Mechanic to fix ASAP | CLOSED | HWO/MTCE |  | available on site | TNPH/MFI/P&A/01/17
| MFI TECON -PNA (HWO) | Ambulance AC not working | AC auto-technician to be dispatched ASAP | CLOSED | MTCE |  | new ambulance on site | TNPH/MFI/P&A/01/17
JULY.29.2017 | MFI NB - RIG 101 | No intrinsically (explosion proof)safe camera to monitor activities at the Rig site. | To get one from the Rig Manager for thr rig use as we get to town. | CLOSED | Tool Pusher/ NBDC MGT Team |  | camera on site | HSE/MFI/06/2017
| MFI NB - RIG 101 | No backup generator at the Rig site minicamp, only one generator has beenrunning day andnight | A pre mob back up generator should be sent from ASAP to avoid power failure | CLOSED | Tool Pusher/ NBDC MGT Team |  | Available on site | HSE/MFI/06/2017
| MFI NB - RIG 101 | Observed a proper job hazard analysis was done by the Rig electrical team before carrying outa routine electrical maintenance at the rig site. | A goodpractice and commendable effort but they need to apply PTW & LOTO system to isolate all exposed electrical energy. | CLOSED | Chief Electrican/GZS |  | Available on site | HSE/MFI/06/2017
| MFI NB - RIG 101 | Drop objects field survey is yet to be completed by JC international | We need to invite them to conclude andclose this survey ASAP | CLOSED | Tool Pusher/ Ewa |  | available on site | HSE/MFI/06/2017
| MFI NB - RIG 101 | No sandbags to lag the safe heaven inside the Rig site. | We need to get the safe heaven ready in case of any emergency | CLOSED | Dsv/GZS/RSS |  | Available on site | HSE/MFI/06/2017
| MFI NB - RIG 101 | The sport receational room is used as store to keep unrepaired electrical /pumping items | A dedicated store room should be provided for the camp coordinator to keep such loads andcrtical spares | CLOSED | Camp coordinator |  | room now being used for safety meeting | HSE/MFI/06/2017
| MFI NB - RIG 101 | No container to accommodate the Assets control men, when it rains they have no shelter to say at the rig site. | A 10ft container should be provided for the assets control team as their office | CLOSED | Sam Ero/Chris A |  | available on site | HSE/MFI/06/2017
| MFI NB - RIG 101 | Observed some visitors came in to the DSV office without the access team checking & notifying him before letting them in | The RSS need to educate the access control team on how to m free assessof visitors into theRig site without safety briefing. | CLOSED | RSS/Rig HSSE officer |  | available on site | HSE/MFI/06/2017
| MFI NB - RIG 101 | Poor carpentry work done at the store, the resturant, butchery,etc, Wood is of low quality and work is poorly done. | Rig manager to review wood works and send in another carpenter with better quality materials. | CLOSED | Tool Pusher/Camp coordinator |  | a carpenter was brought in to rework the affected parts | HSE/MFI/06/2017
| MFI NB - RIG 101 | The new changing room floor is yet to be fixed with floor tiles and the A/c is bad | Need to fix the carpet tiles and the bad A/C as well as the cupboard so that it will be fixed for purpose ASAP | CLOSED | Tool Pusher/Camp coordinator |  |  | HSE/MFI/06/2017
| MFI NB - RIG 101 | Several water heater leakages, roof leakagesandbad floor tiles were recorded at the campsite facilites like the recreation, the sport room etc were all leaking. | Plumber and electrity utility technican need to be placed on Board to fix some of these things ASAP | CLOSED | Tool Pusher/Camp coordinator |  |  | HSE/MFI/06/2017
| MFI NB - RIG 101 | More single beds are needed as the double bunks provided are not fit for purpose to be used. | Single beds should be supplied from town to get the SPDC crew members fully accommodated ASAP | CLOSED | Tool Pusher/Camp coordinator |  |  | HSE/MFI/06/2017
Dec.15.2015 | MFI TECON -PNA (HWO) | Some electrical sockets are exposed and is not safe | Electrical sockets should not be exposed to rain/ sun | CLOSED | Rig Electrician/Rig Manager |  |  | HSE/MFI/05/2015
| MFI TECON -PNA (HWO) | Spillage on the main diesel tank arena | The two electric pumps for the main diesel tank needs to be repaired to control the spillage | CLOSED | Maintenance manager/Rig Manager |  |  | HSE/MFI/05/2015
| MFI TECON -PNA (HWO) | No steam wash/pressure wash for engines and generator | Steam wash/pressure wash for engines and generators should be available at rigsite | closed | Rig Manager |  |  | HSE/MFI/05/2015
| MFI TECON -PNA (HWO) | Leakage of hydraulic from the hydraulic power pack. And there is no back up for the hydraulic | The back up hydraulic power pack is not functional and the main pumps are bad | closed | Maintenance manager/Rig Manager |  |  | HSE/MFI/05/2015
| MFI TECON -PNA (HWO) | No air-condition in the store house and (P&A Store house) | 1.5HP air-condition that is meant for both units had been sent out for maintenance for the past 3wks, it should be returned back to the rig for usage | closed | Maintenance manager/Rig Manager |  |  | HSE/MFI/05/2015
| MFI TECON -PNA (HWO) | No secondary retainers for some electric lamps | Secondary retainers should be fix for all the electric lamps | CLOSED | Rig Electrician/Rig Manager | Sight retainers on lapms |  | HSE/MFI/05/2015
| MFI TECON -PNA (HWO) | No bearing for the wind suck at the rigsite | The bearing should be fix to enable it function properly | CLOSED | Rig Manager/HSE Manager |  |  | HSE/MFI/05/2015
| MFI TECON -PNA (HWO) | Medical Emergency for rescue at height procedure yet to be signed by ED Operations | All procedures to be approve by the ED Operations to make it a workable documents | CLOSED | HSE Manager |  |  | HSE/MFI/05/2015
| MFI TECON -PNA (HWO) | Generator Mikano MK3 114KVA trips off occasionally, and trouble shooting is difficult because the panel is not functional | Proper maintenance should be carried out on the generator, the panel needs to repaired for effective trouble shooting | CLOSED | Maintenance Mgr |  |  | HSE/MFI/05/2015
| MFI TECON -PNA (HWO) | Mikano 60KVA Generator has over heating problem, radiator needs flushing (steam Cleaning) | We recommend steam cleaning and a spare top gaskets | CLOSED | Maintenance Mgr/Rig Mgr |  |  | HSE/MFI/05/2015
| MFI TECON -PNA (HWO) | Control valve for counter balance is bad | The Control valve for the counter balance should be replace | CLOSED | Rig Mgr |  |  | HSE/MFI/05/2015
| MFI TECON -PNA (HWO) | Poor maintenance of the operational bus | The Operational bus should be properly maintained | ongoing | Maintenance Mgr |  |  | HSE/MFI/05/2015
| MFI TECON -PNA (HWO) | Lyster Fork lift has been down for the past one month, and tecon had gone to hire and paying more than the agreed contract arrangement with Shell | The Lyster fork lift needs to be repaired. However if tecon wants to hire, the money should not be above the agreed contract arrangement with shell | CLOSED | ED Operations/Business Development Manager/Maintenance Mgr | third party Forklift truck on site |  | HSE/MFI/05/2015
Sep.23.2015 | MFI NB - RIG 101 | Absence of adequate communication facility at the camp site | To be fixed by SPDC | CLOSED | SPDC |  |  | HSE/MFI/04/2015
| MFI NB - RIG 101 | Some night movement are made without police escort from the Rig site to the Campsite. | All night journeys from the rigsite must be undertaken with Police Escort. | CLOSED | SPDC/Tecon |  |  | HSE/MFI/04/2015
| MFI NB - RIG 101 | A farm is situated at the rig site | The villagers should be discouraged from farming in the rig premises. | CLOSED | SPDC | rig move to another site |  | HSE/MFI/04/2015
| PTW Form - Idendified hazards | Observed that hazards in some of the PTW form hazards were not identified. | Hazards identification should be carried out and marked in the PTW form | CLOSED | HSE officer/Goal Zero officer |  |  | HSE/MFI/02/2015
| Transparent PTW tracking bag | Observed that there is no transparent bag for tracking PTW on site where the job is being done. | Transparent tracking bag should be made available | CLOSED | HSE Manager |  |  | HSE/MFI/02/2015
| PTW Distribution | Observed that the PTW distribution is not well understood by the personnel | Awareness on the distribution of the PTW form should be carried out | CLOSED | HSE Manager/rig supervisor |  |  | HSE/MFI/02/2015
| Monitoring of PTW | Observed that the PTW process is not being monitored | PTW process should be monitored for effective performance | CLOSED | HSE Manager/Tool Pusher |  |  | HSE/MFI/02/2015
| No display of PTW certified holders | Names of PTW certified personnel were not displayed. | Names of personnel to sign the PTW should be displayed in the offices of the DS, rig supervisor and HSE office | CLOSED | HSE officer/Tool pusher | Displayed on notice bord |  | HSE/MFI/02/2015
| PTW filing system | Observed that the box files were not used in filling the used PTW forms | Box files should be provided | CLOSED | HSE Manager/Tool pusher | filled ptw forms on site |  | HSE/MFI/02/2015

## INT. AUDIT TRACKER
Colour/ Key On Action Sheet
VERIFIED CLOSED
ONGOING
OPEN
OVER DUE( past due date)
ACTION TRACKING REGISTER
Date Raised | Due Date | Originator (Source) | Findings | Recommended action | Status/closeout date | Action Party | Action taken | Evidence | Reference No
Action Required
INTERNAL HSE AUDIT
|  | C Security | Absence of mirrors and radios and availability of only 3 torches for a sizeable number of staff | Procure additional torches and ensure they are functional and distributed | OPEN
|  | C Security | Non-compliance to PPE usage by personnel in hazardous areas | Re-train all designated personnel on PPE requirements and enforce compliance through supervision and disciplinary measures | OPEN
|  | C Security | Lack of awareness and visibility of Tecon HSE Policies | Conduct HSE policy awareness sessions for all security staff and post updated policies at all security posts and common areas | OPEN
|  | C Security | Standard Operating Procedures were not sighted | All operational procedures must be available at required points | OPEN
|  | C Security | The access team does not have a mobile celephones, although there is an open communication line | Procure and distribute two-way radios to all key security posts and include radio checks in daily routines | OPEN
|  | C Security | All informations are logged in a single book and are not very legible | Every recorded information must be legible | OPEN
|  | C Security | Incidents are not properly documented. | Ensure all incidents are reported, recorded, investigated and properly documented | OPEN
|  | C Security | Emergency drills are conducted but not documented | Conduct emergency drills on schedule, record observations in drill sheets & communicate | OPEN
|  | C Security | No emergency contact displayed at the posts | Paste all emergency contacts at strategic points | OPEN
|  | C Security | Training certificates were not sighted | Ensure all training sessions are documented with signed attendance and certificates issued and maintain a training file for each staff | OPEN
|  | C Security | Some of the CCTV Cameras are not working | Repair or replace non-functional units and implement a maintenance schedule | OPEN
|  | C Security | The fallen part of the fence at WSDS is yet to be fixed | Prioritize repair of the fallen structure and conduct safety inspection to prevent recurrence | OPEN
|  | MTC | PTW Violation on critical task | Risk assessments which includes PTW execution must be done before hazardous tasks | OPEN
|  | MTC, Fishing & Jar | Confirmed TBT Records were sighted but not properly documented | Standardize TBT templates and train supervisors on proper documentation and filing | OPEN
|  | HR, MTC, Fishing & Jar | HR personnel are not trained in accordance to the HSE Training plan sighted; No HSE training carried out in Maintenance, Fishing & Jar dept | Include HR staff in upcoming Relevant HSE training sessions and emphasize their role in onboarding and compliance. Prioritize critical topics like emergency response and hazard identification | OPEN
|  | HR, MFS, MTC, Fishing & Jar | Obsolete organogram sighted; Although, Fisherman job decription sighted | Update the organizational chart to reflect current structure and share with all departments. | OPEN
15th - 17th & 20th Oct, 2025 |  | HR, MFS, SECURITY CONTRACTORS | No standby vehicle to evacuate personnel in the event of an emergency | Designate a dedicated emergency response vehicle, conduct regular readiness checks(quarterly) and include it in the ERP | OPEN
|  | QHSE | Presence of HSE action trackers for audits, drills, mfe, incident reporting but closeout evidence is missing in incident tracker | Update the tracker format to include verification fields | OPEN
|  | QHSE | QHSE Procedures are not known by a number of staff | Conduct refresher training and include QHSE procedures in onboarding, GQHSE Meetings and toolbox talks | OPEN
|  | QHSE | Monthly UAUC targets are not been met consistently as observed in the2025 obectives and targets analysis sheet | Set realistic, department-specific UAUC targets, monitor monthly and provide feedback during GQHSE meetings | OPEN
|  |  | No sighting of Maintenance plan, however, a note stating all tubulars and downhole tools will be re-inspected was seen | Develop and implement a documented maintenance plan which include schedules, responsibilities, and verification mechanisms | OPEN
|  |  | Toolbox Meeting Folder TN/WS/DS/0028TBT sighted indicating meetings are held but Safety Speaker column is unendorsed | Ensure all meeting records are fully completed and endorsed by responsible personnel | OPEN
|  |  | Unendorsed departmental training plan sighted | Review and formally endorse all training plans and assign responsibility for implementation and tracking | OPEN
|  |  | Job description for documentation officer differs from organogram title | Align job titles across documents and update organogram accordingly | OPEN
|  |  | Hardcopy QHSE policies sighted were not pasted, although, signed policy manual was sighted | Display current QHSE policies in all departments and ensure visibility and accessibility for all staff | OPEN
|  |  | Defective pipes incident at Aradel Ogbelle Rig Site was not investigated | Investigate all incidents promptly and document findings and corrective actions | OPEN
|  |  | End of project reviews are done with client but not or informally done internally | Institutionalize internal project performance/close-out reviews, document outcomes to capture/integrate lessons learned | OPEN
|  |  | Schedule of available Maintenance plan are not adhered to | Enforce compliance with maintenance plans through automated reminders and supervisor accountability | OPEN
|  |  | Closeout cannot be verified due to absence of corrective action log or tracker | Create a centralized corrective action register to track findings, assign responsibilities, and verify closeouts | OPEN
|  |  | August 2025 Departmental manual, Equipment mobilization process (tcn dtr dp 02) and power unit (tnc 22 pu) standard checklist sighted but delivery ticket not seen | Ensure all supporting documents (e.g., delivery tickets) are attached to mobilization records | OPEN
|  |  | Difficulty of Document retrieval and poor filing system | Implement a structured document control system (digital or physical) with indexing and access protocols | OPEN
|  |  | Defective table in use | Ensure adequate work station and environment | OPEN
|  |  | HSE Critical Staff and task are not documented | Identify and document all HSE-critical tasks per role and integrate into job descriptions and training. | OPEN
|  |  | NO TRAINING PLAN / MATRIX as well as evidence of inhouse training | Develop a comprehensive training matrix and schedule regular in-house HSE and technical training sessions | OPEN
|  |  | MTCE SUPV SIGHTED IN SOFT COPY JD BUT MTCE HEAD IN ORGANOGRAM | Align job descriptions with current organogram and ensure all JDs are signed and dated. | OPEN
|  |  | Knowledge of and miscommunication of Golden Hse rules as 12 instead of 10 while only one Human resources and Maintenance staff knows the golden rules and none has knowledge of the life saving rules | Organize mandatory refresher training on the Golden & Life-Saving Rules, re-communicate the full set of 12 Golden Rules via posters, digital boards, and toolbox talks and display visual reminders in common areas | OPEN
|  |  | Interviewed staff was not aware of his HSE Responsibilities | Conduct awareness sessions and include HSE responsibilities in job descriptions and onboarding | OPEN
|  |  | HSE Performance targets are not set for staff | Set monthly HSE targets via the appraisal system and monitor compliance | OPEN
|  |  | Inadequate reflection of HWU Warehouse & Jar inventory (in &out) status for all the items in real time while outdated Inventory sighted in Maintenance dept | Implement a digital inventory management system with real-time tracking of item movement. Assign responsibility for inventory updates, conduct monthly audits and reconcile discrepancies | OPEN
|  |  | Date dicrepancies noted in King Jaja hwu ancilliary equipment preventive maintenance schedule tcn-qf-5.7.8B REV 2 24TH May 2021 | Standardize maintenance schedule formats and ensure version control, along with, conducting periodic audits for accuracy | OPEN
|  |  | No recommendation and evidence in sighted NCR Tracker for King Jaja 340k, Drill Safe and Action List -King Jaja | Revise NCR tracker format to include root cause, corrective action, responsible person, and closeout evidence | OPEN
|  |  | Outdated work procedures seen in 2009 departmental manual and TOTAL operations monitoring and tripping Procedures, CWOP Form not sighted in new hwo operations manual; Work procedure sighted but not all on activities in MTC | Include all required forms in the updated manual and cross-reference them in procedures | OPEN
|  |  | Obsolete signed Critical task position sighted, nevertheless, Jack operator and Field Engrs are cognizant of their roles | Replace with updated/current critical task documentation aligned with current roles and responsibilities | OPEN
|  |  | Limited HWU Personnel for operations, as well as insufficient Mechanics and Jack operators, hence, learning on the job; Limited personnel to work on the jar | Conduct a manpower gap analysis and recruit or train additional personnel to meet operational demands. | OPEN
|  |  | Job description of Jack Operator, Tecon, HWO, WSDS and Casing Departmental organogram sighted but not dated, approved and signed, names not included | Update organogram with date, revision, and authorized signatures to reflect current structure and ensure alignment with job titles | OPEN
|  |  | Smoke detectors not availiable in the offices | Install smoke detectors in all office areas and include them in routine safety inspections and maintenance logs | OPEN |  |  | Observation
|  |  | HSE Staff Handbook was not issued to all Staff | Distribute updated HSE handbooks to all employees and maintain issuance logs and confirm acknowledgment | OPEN |  |  | Verification by two(2) HWO personnel
|  |  | Observed HSE objectives not pasted in the office, not sufficiently known (only known by two HWO and one HR staff, not known by 3 interviewed MFS, 2 Fishing & Jar personnel) | Display updated HSE objectives and policies in all work areas and conduct awareness sessions on HSE objectives, integrate HSE objectives into onboarding and operations, review them during toolbox talks and inductions | OPEN |  |  | Staff Interview
|  |  | Obsolete copies of HSE Policies were pasted in the office, although these policies are known | Conduct departemental tour/inspection to ensure updated records are maintained | OPEN
|  |  | Management staff do not participate or barely perform STOP reporting; STOP reporting participation is generally very poor | Reintroduce stop card campaigns, assign STOP card quota to management, set monthly targets, recognize active reporters to drive participation and include participation in performance evaluations | OPEN |  |  | Review of STOP cards
|  |  | Low safety meeting attendance by Subordinates; Staff attendance isn't monitored | Track attendance, investigate root causes of absenteeism and reinforce accountability through line supervisors. | OPEN |  |  | Observation during Safety Meeting
|  |  | Absence of HODs and Rig Manager in HSEMS Performance Review, HSE meeting due to Chevron meeting and regrets not sent in; only one HSE meeting attendance by Mr. Sunny in 2025; Poor visible leadership commitment | Reinforce leadership accountability by mandating attendance/formal delegation at HSEMS, Performance review & safety meetings, as well as implement a system for regrets submission with proper justification, track participation and escalate repeated absences | OPEN |  |  | Observation
17TH OCT 2024 |  |  | No record of incident reporting | Increase awareness on incident reporting and sharing of LFIs | CLOSED, Ongoing |  |  | Incident Report/ Investigation Folder
|  |  | No Sighting of eyewash station | Erect eye wash station and communicate | CLOSED |  |  | HWO Warehouse & General warehouse
|  |  | Personnel sighted in worn out coveralls and safety shoes due to no issuance for the year. | Company to provide PPE ASAP for all personnel | CLOSED |  |  | Observe personnel at work site
|  |  | Personnel with responsibility for HSE critical task are not identified or listed | Contractual requirement should be followed and roles and responsibilities developed and communicated to staff | CLOSED |  |  | MOC PROCEDURE ROLLEF
2024-06-20 |  |  | Front head lamps (driver's side) is expired | Front head lamps (driver's side) should be replaced | CLOSED |  | Head lamps were replaced | Maintence form
|  |  | Body of vehicle is in bad shape | Body of vehicle should be taken for maintenance | CLOSED |  | Proper maintenance was carried out | Maintence form
FEB. 2024 |  | FIELD | Most window & A/C Rain protectors are damaged | A/c needs replacement | CLOSED |  | The A/C's were all serviced and are very functional | JOB COMPLETION FORM
|  | FIELD | Observed a broken security light outside the cabin | Security light need to be fixed | CLOSED |  | Security light were light | PICTURE
|  | FIELD | Floor surface not with uniform level and different tiles. | Floor surface need to be made with same tiling all through | CLOSED |  | The floor was properly retiled and maintenace was carried out | PICTURE
|  |  | The internal wall painting is dirty and full in colour | The internal wall need washing & re painting with a brighter colour | CLOSED |  | the walls were all repainted and proper maintenance was carried out | PICTURE
2023-10-04 |  | Logistics | Operation requires lifting belts, but there is none | To procure lifting belts | CLOSED |  | Lifting belts were purchased | PICTURE
|  | Logistics | Forklift Operator doesn’t have a valid IADC certificate. 1 certified PIC. | Forklift operator (Dike)’s IADC certification to be renewed. some personnel should be booked for PIC certification. | CLOSED |  | Oprerators IADC were renewed | Certificates
|  | QA/QC | Bad slings seen in basket | Discard properly | CLOSED |  | Unusable slings are quarantined and cut in pieces | PICTURE
|  | ,QA/QC | No storage bin for scrapped lifting accessories | To provide Waste bin for temporary storage of unusable slings, belts, shackles, etc., before disposal | CLOSED |  | Unusable slings are quarantined and cut in pieces | PICTURE
|  | Logistics | No written plan in place for cold stack maintenance,cold stack maintenance is project based prior to mobilization to site | A cold stack maintenance plan should be developed and put to use | CLOSED |  | Maintenance plan has been developed | Maintenance plan
|  | Logistics | The process to tag equipments for repaairs or junk is not in place | Process to be developed | CLOSED |  | Equipment on repairs are boldly tagged | PICTURE
|  | Logistics | There is no enough storage space for some of the equipment in the caravan/ store against corrosion | More storage facility to be provided for storage of equipment against corrosion | CLOSED |  | Requisition on more storage space | Requisition
|  | Logistics | Inventory records not available | Comprehensive equipment inventory records to be develpoed | CLOSED |  | Comprehensive inventory records were developed | Soft copies
2022-08-21 |  |  | Absence of hazard documentation for risky task | Develop a comprehensive hazard register for all activities | CLOSED |  | Hazard register was developed and distributed to all departments | HSE CASE: PART 4 : RISK MANAGEMENGT
|  |  | Personnel sighted in worn out coveralls and safety shoes due to no issuance for the year. | Company to provide PPE ASAP | CLOSED |  | Personnel yearly PPEs are issued as at when due | 2015 PPE Distribution list
|  |  | Team is not aware of Management of Change Procedure and have on process form for practicing it. | All safety critical changes to task must undergo MOC planning and approval before execution. The HSE team recommended to provide a typical sample form for them and educate them on how to use it. | CLOSED |  | MOC procedures were handed over to HOD's which are Supervised by QAQC | MOC rolled out during HSE meeting and procedures issued to depts.
|  |  | Personnel with responsibility for HSE critical task are not identified or listed, Absence of signed copies of Job description for staff | Contractual requirement should be followed and roles and responsibilities developed and communicated to staff. Responsible parties to endorse copies | CLOSED |  | Personnel with responsibility for HSE critical task are clearly identified and all signed copies of Job description for staff available | HSE CASE: PART 4 : RISK MANAGEMENGT
APR. 2022 |  |  | No evidence of use of PTW in the department | Key personnel should be PTW certified and forms issued for all Hot Work or other highly hazardous work and pasted on a PTW board | CLOSED |  | More PTW holders were trained and awareness training are carried out at interval | Training certificates and filled PTW
|  | ALL Departments | IT students sightedworking without PPE | PPE should be provided for IT Stiudents | CLOSED |  | All It students are issued PPE immediately after safety induction | PPE issued to staff
|  | ALL Departments | Personnel are aware of waste segregation. However, implementation is undone. | Increase awareness Waste segregation and Environmental/waste management policy and place policies in offfices. | CLOSED |  | Presentation was carried out in the general safety meeting of the importance of waste segregation | Waste management awareness during general hse meeting and displayed in offices
8TH OCT. 2021 |  | All Departments | There is awareness but emergency procedures are not placed at strategic points | Emergency Response team and Procedures for fire, community invasion, medevac should be pasted at strategic places | CLOSED |  | The emegency procedures were developed sent across the various departmental and also pasted on the notice board | noticeboard
|  | ALL Departments | HSE audit reports are kept at the central HSE office not | copies of all Audit report should be filed in audited department | CLOSED |  | All audit reports are distributed to the concerned departments for reference purposes | The distribution list
|  |  | Site Is well arranged but faulty equipment are not properly labelled & arranged | Faulty / Damaged tools should be tagged and segregated | CLOSED |  | All faulty equipment are properly quarantined separately | scrap area identifies and scrapd labelled & segregated
|  |  | Training needs and requirements are not prepared and personnel are not technically trained and there is no evidence of on the job training | Training plan for HSE critical positions should be developed, implemented and training certificates filed | CLOSED |  | The training plan has been developed | A copy of the training plan
|  | ALL Departments | There is no standout document defining each staff safety role & responsibility at the department leveL. | Safety roles and responsibilities for postions should be develpoed and issued to staff | CLOSED |  | This has been implemented | Attendance list
03.03.2021 |  | Logistics | Equipment status identification with the use of stickers ( Red- Equipment in bad state, Yellow - Equipment under repairs and Green - Equipment ready for use) is not in place | Equipment status identification with stickers to be activated | CLOSE |  | Identification sticker for equipment stautus were activated | PICTURE
03.03.2021 |  | Logistics | Management of Change is not being implemented |  | CLOSED |  | Management of change procedures were implemented by the personnel involved | Fiiled MOC
03.03.2021 |  | Logistics | Investigation system in case of missing/damaged tools and accident due to equipment failure is in place but report not sighted | Investigation report and tool missing/fault report forms to be developed and put to use | OPEN |  | The SHDEM HOD was asked to develop this
03.03.2021 |  | Logistics | Inadequate manpower | Employment process to be as well activated | CLOSED |  | Some personnel were employed | Employment Letter
03.03.2021 |  | Logistics | Training gap ( No evidence of training Matrix/ Plan) | Training matrix to be developed and implement as per training needs and requirements | CLOSED |  | In- House training plan was developed | Training plan
03.03.2021 |  | Logistics | Manual maintenance records/tracker and electronic preventive maintenance system tracker which is 50% functional now | PMS system to be enhanced and made to cover all reas of operations as 100% implementation | OPEN |  | Requisition on a well developed PMS | Requisition
03.03.2021 |  | Logistics | No written plan in place for cold stack maintenance,cold stack maintenance is project based prior to mobilization to site | A cold stack maintenance plan should be developed and put to use | CLOSED |  | Maintenance plan has been developed | Maintenance plan
03.03.2021 |  | Logistics | The process to tag equipments for repaairs or junk is not in place | Process to be developed | CLOSED |  | Equipment on repairs are boldly tagged | PICTURE
03.03.2021 |  | Logistics | There is no enough storage space for some of the equipment in the caravan/ store against corrosion | More storage facility to be provided for storage of equipment against corrosion | CLOSED |  | Requisition on more storage space | Requisition
03.03.2021 |  | Logistics | Inventory records not available | Comprehensive equipment inventory records to be develpoed | CLOSED |  | Comprehensive inventory records were developed | Soft copies
2019-10-09 |  | Logistics | 1 new strap belt sighted. Not in use and not certified. Observed Truck XX354PHC without strap belt/tie rope. | To be procured and certified. All trucks to have strap belt/tie rope. | CLOSED |  | New strap belts and tie ropes were purchased | PICTURE
2019-10-09 |  | Logistics | Not regular/up to date. Also not properly filed. | One folder each be dedicated to forklift, crane and trucks. And filed regularly | CLOSED |  | Proper daily checklist carried out on different heavy duty equipments | PICTURE
2019-10-09 |  | Logistics | Operation requires lifting belts, but there is none | To procure lifting belts | CLOSED |  | Lifting belts were purchased | PICTURE
2019-10-09 |  | Logistics | Forklift Operator doesn’t have a valid IADC certificate. 1 certified PIC. | Forklift operator (Dike)’s IADC certification to be renewed. some personnel should be booked for PIC certification. | CLOSED |  | Oprerators IADC were renewed | Certificates
2019-10-09 |  | QA/QC | Bad slings seen in basket | Discard properly | CLOSED |  | Unusable slings are quarantined and cut in pieces | PICTURE
2019-10-09 |  | ,QA/QC | No storage bin for scrapped lifting accessories | To provide Waste bin for temporary storage of unusable slings, belts, shackles, etc., before disposal | CLOSED |  | Unusable slings are quarantined and cut in pieces | PICTURE
2019-10-09 |  | Logistics | under repairs (in complete breakdown, including all 4 tyres)3 Ton Nissan Forklift | To hasten repairs and to certify. | CLOSED |  | Maintenance was carried and certification was done | Maintence form
2019-10-09 |  | 3 Ton Hyster forklift | under repair (not certified, no reverse alarm, engine gets hot, gear problems, oil leakage) | To repair all faults observed and to certify | CLOSED |  | Maintenance was carried and certification was done | Maintence form
2019-10-09 |  | 3 Ton Caterpillar Forklift | Not certified, weak hydraulic pump – unable to lift the FMS and items more than 1 ton, oil leakage, ram drops freely | To repair all faults observed and to certify. | CLOSED |  | Maintenance was carried and certification was done | Maintence form
2019-10-09 |  | Telescopic Forklift | Tilts down on its own with heavy loads | Repair tilting faults | CLOSED |  | Repair tilting faults was carried out | Maintence form
|  |  | No lights, no wiper, no side mirror, no reverse alarm. | Carry out repair of all faults observed on forklift | CLOSED |  | Maintenance was carried | Maintence form
2019-10-09 |  | Tailor Forklift | Some lights are not working, no reverse alarm | Carry out repair of all faults observed on | CLOSED |  | Maintenance was carried | Maintence form
|  |  | Forklift is not certified | Have forklift certified | CLOSED |  | Procedure on forklift certification was carried out and it was certified | Certificate
2019-10-09 |  | OVERHEAD CRANE | Operation requires overhead cranes in both the main workshop and workshop extension. There is none | To install overhead crane for the main workshop and to complete the installation of the overhead crane started in the workshop extension | CLOSED |  | overhead cranes were provided for both the main workshop and workshop extension. There is none | PICTURE
|  |  | 1 in external workshop not installed | To be installed. | CLOSED |  |  | PICTURE
2019-10-09 |  | JIB CRANES | Lifting Belt: Operation requires lifting belts, but there is none | To procure lifting belts | CLOSED |  | New lifting belts were purchased | PICTURE
|  |  | Jib Crane: Both not certified. No load rating, 1 Quarantined. | Jib cranes to be put in order and certified, with load capacity determined | CLOSED |  | Jib cranes status was reported to SHDEM HOD who ensure this were put in order and certified, with load capacity determined | PICTURE
2019-10-09 |  | 35 Ton Link-belt Crane | LMI, not functioning | Possibility of installing LMI on cranes to be looked into. | CLOSED |  | The LMI was repaired | Maintence form
|  |  | Not certified | Records of all inspections be documented and filed properly | CLOSED |  | Certification process and carried out and it was cerified | Certificate
2019-10-09 |  | 30 Ton Groove Crane | Overheats, sometimes can’t complete jobs | Grease the wire ropes | CLOSED |  | Proper maintenance was carried out | Maintence form
|  |  | Brakes (for movement), not active (dangerous!) | Have at least the hook blocks, the sheaves and the wire ropes certified | CLOSED |  | Proper maintenance was carried out | Maintence form
|  |  | LMI, not functioning | Carry out all repairs | CLOSED |  | The LMI was repaired | PICTURE
|  |  | Not certified | At least one of the cranes should be equipped and certified for man riding. | CLOSED |  | The crane was maintained and was certified | PICTURE
14/12/2018 |  | VEHICLE AUDIT | Air- conditioner is not working effectively | Air - conditioner should be repaired | CLOSED |  | A new air condition was purchased | PICTURE
|  | GUC 38 SV, XX 355 PHC | All the roller belts(AC/alternator/Power Steeringbelts) are showing signs of weakness/tear. | All the roller belts(AC/alternator/Power Steeringbelts) are showing signs of weakness/tear and should be changed out immediately | CLOSED |  | All the roller belts(AC/alternator/Power Steeringbelts) were changed out immediately | PICTURE
|  | GUC 38 SV, XX 355 PHC | Rear lights are expired and broken | The Rear lights needs to be replaced | CLOSED |  | Proper maintenance and rear light was replaced | Maintence form
|  | XX 354 PHC, JJ94 AE | Anxillary Assembly (4 x 4 capability/option) for this vehicle has been disconnected. | Anxillary Assembly (4 x 4 capability/option) for this vehicle should be connected. | CLOSED |  | Vehicle's anxillary assembly was fixed | Maintence form
|  | BDG 286 AC, XX 353 PHC | Front head lamps (driver's side) is expired | Front head lamps (driver's side) should be replaced | CLOSED |  | Head lamps were replaced | Maintence form
|  | PBT 414 XA, PBT 477 XA | Body of vehicle is in bad shape | Body of vehicle should be taken for maintenance | CLOSED |  | Proper maintenance was carried out | Maintence form
|  | JJJ 94 AE, XC 283 WWR | Engine oil leakage | Engine oil leakage should be repaired | CLOSED |  | Engined oil was changed | Maintence form
|  | GGU 38 VS, KTU 12 ES | Tractor tyres are bad | New Tractor tyres should be provided | ONGOING |  | Already purchased tractor tyres was fixed | JOB COMPLETION FORM
|  | XX 354 PHC, JJ94 AE, KTU 12 ES | Observed windscreen/windom washer are not in good shape | Windscreen/windom washer should be replaced. | ONGOING |  | Replacement of windscreen | JOB COMPLETION FORM
|  | GUC 38 SV, XX 355 PHC | Fire extinguisher are expired | Fire extinguisher should be serviced/ replaced | CLOSED |  | A tracker on serviced and next servicing date well developed | CERTIFICATE
|  | XX 354 PHC, JJ94 AE | First aid box needs to be equiped | First aid box should be well equiped | CLOSED |  | First aid boxses were well equiped and regularily inspected | PICTURE
|  | XX 354 PHC, JJ94 AE, KTU 12 ES | Head light not lighting well | Head light needs replacement | CLOSED |  | The headlight was replaced immediately | JOB COMPLETION FORM
|  | XX 354 PHC, JJ94 AE, KTU 12 ES | No coolant in the radiator (only water seen) and Coolrant reservior cover missing and covered with b | The coolant in the radiator should be refilled and Coolrant reservior cover needs replacement. | CLOSED |  | The coolrant reservior was replaced and radiator was changed | JOB COMPLETION FORM
|  | GUC 38 SV, XX 355 PHC | Battery terminal head not seating well. | Battery terminal head should be worked on. | CLOSED |  | Proper maintenance was carried and battery terminal was changed | JOB COMPLETION FORM
|  | XX 354 PHC, JJ94 AE, KTU 12 ES | Vehicles inner lights and radio are not working, the seats are torn and needs refolding | Vehicles inner lights and radio should be repaired, new seats clothing should be provided. | CLOSED |  | The vehicle was sent for proper maintenace where all the listed were changed immediately | JOB COMPLETION FORM
|  | XX 354 PHC, JJ94 AE | Front bumper is pulling off. | Front bumper should be replaced. | CLOSED |  | The fronter bumper was quickly replaced | JOB COMPLETION FORM
22/11/2018 |  | PNA ACCOMMODATION/CATERING CABINS | Window net very dirty with insects trapped between the glass door & the window net frame. | The window net should be open and trapped insects clean thoroughly/ outright replaced for damages ones | CLOSED |  | All damaged nets were replaced with new ones | JOB COMPLETION FORM
|  |  | Noticed faulty external industrial socket for powering the cabin | The socket need to be fixed or replaced with a better one | CLOSED |  | A new socket was installed | JOB COMPLETION FORM
|  |  | Observed blue alumium facial board on the cabin top damaged all around | The damaged aesthetics Alumium facial board need to be changed out | CLOSED |  | A new aesthetic alumium board was provided | JOB COMPLETION FORM
|  |  | Most window & A/C Rain protectors are damaged | A/c needs replacement | CLOSED |  | The A/C's were all serviced and are very functional | JOB COMPLETION FORM
|  |  | Observed a broken security light outside the cabin | Security light need to be fixed | CLOSED |  | Security light were light | PICTURE
|  |  | Floor surface not with uniform level and different tiles. | Floor surface need to be made with same tiling all through | CLOSED |  | The floor was properly retiled and maintenace was carried out | PICTURE
|  |  | The internal wall painting is dirty and full in colour | The internal wall need washing & re painting with a brighter colour | CLOSED |  | the walls were all repainted and proper maintenance was carried out | PICTURE
|  | THE KITCHEN CABIN | The kitchen wooden cabinets are soaked with water and are decaying already | The cabinets should be replaced with alumium type so that they can be preserved better | CLOSED |  | New cabinets were provided | PICTURE
|  |  | Observed only one washing sinkin the kitchen is not enough to handle all washings | An additional wash hand basin should be installed inside the kitchen | CLOSED |  | Provision of additional wash hand basin was made | PICTURE
|  |  | The gas burner has broken leg at the base and its tilted to the floor | The broken legs should be fixed to keep the burner fit for purpose | CLOSED |  | New gas burners were purchased and the broken ones were repaired | JOB COMPLETION FORM
|  |  | The entire electrical wiring for powering the electrical burner not properly trunked | With flying excess armored cable well-kept around | CLOSED |  | The electrical burner was properly trunked | JOB COMPLETION FORM
|  |  | Only one insect catcher found in the entire kitchen | Additional insect catcher is recommendede for the kitchen | CLOSED |  | Insert catcher was provided with spare | PICTURE
|  |  | Exposed fume expeller without a wire qauze | Fuime expeller need to be protected from behind | CLOSED |  | All fume expellers were properly protected | PICTURE
|  |  | The external fume extractor protector is removed | The protector need to be replaced immediately to avoid influx of insects into the kitchen | CLOSED |  | The protector was replaced and spare were made available | JOB COMPLETION FORM
|  |  | Noticed a faulty external industrial socket for powering the kitchen cabin | The socket need to be fixed or replaced with a better one | CLOSED |  | Socket was quickly changed and routine checks are carried out | JOB COMPLETION FORM
29/10/2018 |  | SECURITY | Poor lighting System at the fence and non- functional light working at night | Lighting system should be improved by the maintenance dept. to work at night. | CLOSED |  | Mor lamp holders were install for proper illumination at night | JOB COMPLETION FORM
|  | SECURITY | None of their personnel are currently trained on how to handle unexcepted firefighting situation & first aid of personnel during emergency. | Personnel should be trained on firefighting and first aiders by the Qhse department | CLOSED |  | More personnel were trained on first aids and fire fighting | Certificate of trainings
|  | Logistics | Do have all the emergency kits like first aid box, valid fire extinguishers, spare tyres, triangle refector, wheel spanner etc | First aid and firefighting extinguisher is available in their vehicles but most logistics personnel are not trained on how to handle emergencies. | CLOSED |  | All the emergency kits like first aid box, valid fire extinguishers, spare tyres, triangle refector, wheel spanner were provided for each vehcile etc | FIREFIGHTING CERTIFICATE
|  | Logistics | Do you have a copy of the new company contingency plans with phone contacts for the entire various emergency situations in place? | A copy of the new emergency contingency plans with current phone contact for the various emergency situation in place. | CLOSED |  | Developed a copy of the new emergency contingency plans with current phone contact for the various emergency situation in place. | Tecon Contingency plan
2017-08-10 |  | Logistics, QA/QC | Safe operating procedures for the crane and forklift are not available. Safe working load (SWL) is not inscribed on the Telescopic Forklift. | Procedures should be developed and conspicuously disseminated. The SWL can be inscribed with paint on all lifting equipment | CLOSED |  |  | Inspection Checklist
|  | Logistics | Toolbox talk are not held regularly | JSA is mandatory before commencement of operations. | CLOSED |  |  | Toolbox meeting folders
|  |  | Some of the lifting pad eyes are not colour coded with the current colour code | Request for certification of pad eyes and follow up. | CLOSED |  |  | inspection certficates
|  | QA/QC | Defective equipment are neither identified, tagged , tracked nor segregated/segregation of scraps. | Follow documented procedures in quality manual. Develop policy and procedure for scraps / defective tools. | CLOSED |  |  | scrap area identifies and scrapd labelled & segregated
|  |  | Departmental personnel operate forklift without training / certification | Train at least one Personnel in the department due to the high operational usage of forklift. | CLOSED |  |  | certified operators to carry out task.-Trainng matrix
|  |  | Test certificates for lifting equipments could not be retrieved. | Trace location of test certificate and keep in a technical file. |  |  |  | Test certificate file
|  |  | Poor housekeeping and storage of slings, shackles, etc. | Temporary racks should be welded in WS/DS roofed storage area to accommodate slings. While proper storage facility is constructed. | open
April. 04. 2017 |  |  | Personnel are not aware of 2017 objective/target and their roles towards its realization | Policies, Objective and targets to be pasted in the department and awareness intensified | CLOSED |  |  | Policies pasted in all offices/ notice boards & communicated during TBM
|  |  | Tool box meetings which is a channel of communication has not been done this year. | JSA should be held before commencement of every task | CLOSED, Ongoing |  |  | TBM folders
|  |  | No record of incident reporting | Increase awareness on incident reporting and sharing of LFIs | CLOSED, Ongoing |  |  | Incident Report/ Investigation Folder
|  |  | No Sighting of eyewash station | Erect eye wash station and communicate | CLOSED |  |  | HWO Warehouse & General warehouse
|  |  | Personnel sighted in worn out coveralls and safety shoes due to no issuance for the year. | Company to provide PPE ASAP for all personnel | CLOSED |  |  | Observe personnel at work site
|  |  | Personnel with responsibility for HSE critical task are not identified or listed | Contractual requirement should be followed and roles and responsibilities developed and communicated to staff | CLOSED |  |  | MOC PROCEDURE ROLLEF
|  |  | MOC on Tecon fishing procedure was not sighted | All safety critical changes to task must undergo MOC planning and approval before execution. | CLOSED
Mar. 24. 2017 |  |  | UA/UC are not reported | STOP campaign | CLOSED |  |  | Behavioural safety awareness during general hse meeting
|  |  | No evidence training plan/matrix was sighted since 2015 till date. | An annual Training / Certification Plan should be documented and forwarded to HR & QHSE Department as well as the record of implementation; STOP cards should also be used for On the job training. | OPEN
|  |  | Department Organogram and interview reflects gross shortage of staff to execute enormous maintenance task | More staff should be deployed to enable task efficiency, reduce stress and other ergonomic hazards. | ongoing |  |  | personnel have been sent to some departments and IT recruited to assist
Nov. 27. 2015 |  |  | Poor knowledge of annual objectives, Warri Staff do not have current copies of the safety hand book | To be distributed to all staff,Objectives and policies should be communicated to staff regularly through different means and medium. | CLOSED |  |  | handbooks sent to warri
|  |  | Equipments are not classified according to colours | Equipments should be arranged according to colours and monitored regularly
|  |  | Staff are not aware of the MOC procedure, MOC for change on Tecon Lifting Plan procedure for Apara 001 was not sighted | MOC should be communicated to staff and department issued procedure and monitored for execution | CLOSED |  |  | MOOC rolled out during HSE meeting and procedures issued to depts.
|  |  | Training plan / record not comprehensive. No in-house training has been done in 2015, Trainings are only done as per client requirement | An annual Training / Certification Plan should be documented as well as the record of implementation | CLOSED |  |  | Training plan integrated into HSE training plan
|  |  | Non functional remote shut down switch on the basket which is a 2nd alternative safety device | Replace control valve switch ASAP | CLOSED |  | Control valve switch was changed immediately | 340k basket
|  |  | Absence of hazard documentation for risky task | Develop a comprehensive hazard register for all activities | CLOSED |  | Hazard register was developed and distributed to all departments | HSE CASE: PART 4 : RISK MANAGEMENGT
|  |  | Personnel sighted in worn out coveralls and safety shoes due to no issuance for the year. | Company to provide PPE ASAP | CLOSED |  | Personnel yearly PPEs are issued as at when due | 2015 PPE Distribution list
|  |  | Team is not aware of Management of Change Procedure and have on process form for practicing it. | All safety critical changes to task must undergo MOC planning and approval before execution. The HSE team recommended to provide a typical sample form for them and educate them on how to use it. | CLOSED |  | MOC procedures were handed over to HOD's which are Supervised by QAQC | MOC rolled out during HSE meeting and procedures issued to depts.
|  |  | Personnel with responsibility for HSE critical task are not identified or listed, Absence of signed copies of Job description for staff | Contractual requirement should be followed and roles and responsibilities developed and communicated to staff. Responsible parties to endorse copies | CLOSED |  | Personnel with responsibility for HSE critical task are clearly identified and all signed copies of Job description for staff available | HSE CASE: PART 4 : RISK MANAGEMENGT
|  |  | No Sighting of eyewash station | Erect eye wash station and communicate | CLOSED |  | Eye wash stations has been installed at the specific areas | erected at general W/house & HWO Warehouse
|  |  | Tool Box Talk are sparingly held as documented evidence for some months are absent | Monitoring and staff reorientation of importance of toolbox talk, Workers should always hold pre job safety meetings before commencing their operations | Ongoing |  | Daily tool box meetings are held and supervised by QHSE personnel which are properly documented | TBM folders
June 4. 2015 |  | ALL Departments | No Evidence of HSE laws, regulations and requirements, non awareness of NFA, DPR etc. | Safety laws and compliance awareness should be communicated to all employees and documented copies should be filed | CLOSED |  | Evidence of HSE laws, regulations and requirements, and awareness of NFA, DPR were communicated in the Monthly safety meetings | Lws & regulations folder
|  | All Departments | No evidence of HSE Policies and Targets for 2015. | Tecon Policies/Plan awareness should be communicated to staff during Safety meetings, display in all offices and issued to contractors. Major contractors policies should also be obtained. | CLOSED |  | The HSE policies and targets were developed and sent across all the departments | Issuance list and HSE noticed boards
|  | ALL Departments | Inventory records are available but not updated regularly | Soft and Hard copies of inventory should be maintained and personnel designated to track, monitor and update timely | CLOSED |  | Effeciency in updating inventory records were encouraged | Soft & hard copies available in dept. files
|  | Machine shop, HWO, maintenance | No evidence of use of PTW in the department | Key personnel should be PTW certified and forms issued for all Hot Work or other highly hazardous work and pasted on a PTW board | CLOSED |  | More PTW holders were trained and awareness training are carried out at interval | Training certificates and filled PTW
|  | ALL Departments | IT students sightedworking without PPE | PPE should be provided for IT Stiudents | CLOSED |  | All It students are issued PPE immediately after safety induction | PPE issued to staff
|  | ALL Departments | Personnel are aware of waste segregation. However, implementation is undone. | Increase awareness Waste segregation and Environmental/waste management policy and place policies in offfices. | CLOSED |  | Presentation was carried out in the general safety meeting of the importance of waste segregation | Waste management awareness during general hse meeting and displayed in offices
|  | All Departments | There is awareness but emergency procedures are not placed at strategic points | Emergency Response team and Procedures for fire, community invasion, medevac should be pasted at strategic places | CLOSED |  | The emegency procedures were developed sent across the various departmental and also pasted on the notice board | noticeboard
|  | ALL Departments | HSE audit reports are kept at the central HSE office not | copies of all Audit report should be filed in audited department | CLOSED |  | All audit reports are distributed to the concerned departments for reference purposes | The distribution list
|  |  | Site Is well arranged but faulty equipment are not properly labelled & arranged | Faulty / Damaged tools should be tagged and segregated | CLOSED |  | All faulty equipment are properly quarantined separately | scrap area identifies and scrapd labelled & segregated
|  |  | Training needs and requirements are not prepared and personnel are not technically trained and there is no evidence of on the job training | Training plan for HSE critical positions should be developed, implemented and training certificates filed | CLOSED |  | The training plan has been developed | A copy of the training plan
|  | ALL Departments | There is no standout document defining each staff safety role & responsibility at the department leveL. | Safety roles and responsibilities for postions should be develpoed and issued to staff | CLOSED |  | This has been implemented | Attendance list

## EXT. AUDIT TRACKER
ACTION TRACKING REGISTER
EXTERNAL AUDIT TRACKER
Date Raised | Due date | Originator (source) | Reference NO | Findings | Recommended Action | Action Party |  | Evidence
STATUS
27TH MAY 2024 | 2024-06-07 |  |  | No evidence of management commitment in the company's activities | Provision of signed documents showing management commitment in the operations to be provided | RAY integrated service | Closed | Reviewed HSE Policy Statement
| 2024-06-07 |  |  | Observed there is no existing emergency procedure and plans in place and | Develop and emepergency procedure and plan, communicate and publish it on the HSE notice boards | RAY integrated service | Closed | Sighted Emergency Response Plan
| 2024-06-07 |  |  | Audit Non Conformities are not tracked, hence followup is not done consistenetly. | Deveop a tracker and follow up to ensure open items are closed out as at when due | RAY integrated service | Closed | Sighted an Audit Tracker
| 2024-06-07 |  | TECQHSE/EXT/AUD.R/02/2024 | Observed there is no training plan in place | Develop a training plan and ensure compliance | RAY integrated service | Closed | Annual Training Plan
21ST MAR. 2024 | 2024-04-12 |  | TECQHSE/EXT/AUD.R/01/2024 | Observed there is no retainership clinic for staff | The retainership clinic should be close to the work area ie not more than 15 mins drive | c TEST CONTROL HSE | Closed | Sighted medical retainership agreement with Pamo Cliic
| 2024-04-12 |  | TECQHSE/EXT/AUD.R/01/2024 | Observed no developed and updated training matrix as at the audit time | Training matrix should be developed and updated as at when due | c TEST CONTROL HSE | Closed | Training Matrix sighted
| 2024-04-12 | c TEST CONTROL LIMITED | TECQHSE/EXT/AUD.R/01/2024 | Observed there is no visible muster point | The muster point to be mapped out, made visible and free from obstruction | c TEST CONTROL HSE | Closed | Fit for use muster point
| 30/06/2023 |  | TECQHSE/EXT/AUD.R/01/2023 | Observed the company do not conduct appraisal for drivers | All personnel should be included in the company's appraisal system | H HR | Open
MAR.23RD 2023 | 17/04/2023 | H HAULAGE NIG.LTD | TECQHSE/EXT/AUD.R/01/2023 | Observed incident investigation are not carried out? | Personnel should be trained on incident reports and investigation | H HSE | Closed
MAR.23RD 2023 | 29/03/2023 |  | TECQHSE/EXT/AUD.R/01/2023 | Observed drivers do not have valid fitness to work certification | All drivers should go for medical examination | H HSE | Closed | Sighted Annual Medical Certificate for 3 drivers
MAR.23RD 2023 | 27/03/2023 |  | TECQHSE/EXT/AUD.R/01/2023 | Observed Contractor doesn’t have SWDA Policies | Clients HSE policies must be documented | H HSE | Closed | SWDA Policy Documents have been delivered to Vendor
MAR.23RD 2023 | 24/03/2022 |  | TECQHSE/EXT/AUD.R/01/2022 | Observed there is no fire extinguisher in the work area | Fire extinguisher should be kept in place in case of fire incidence. | SCO | Closed | Sighted DCP and CO2 Extinguishers at strategic locations
MAR.23RD 2023 | 17/03/2022 |  | TECQHSE/EXT/AUD.R/01/2022 | Observed the HSE statistics is not up-to-date | HSE statistics should be updated as at when due | SCO | Closed | Observed Update KPI's
MAR.16 2022 | 20/05/2022 | SCO | TECQHSE/EXT/AUD.R/01/2022 | Observed A UT personnel ASNT level 11 certificate is not available | All the UT personnel should be certified | SCO | Open
| 08.07.2021 |  | TECQHSE/EXT/AUD.R/02/2021 | Observed there is no retainership clinic | RAY to quickly get a retainership clinic as a covery for personnel in the event of an emergency | RAY integrated service | Closed | Sighted retainership agreement
| 08.07.2021 |  | TECQHSE/EXT/AUD.R/02/2021 | Observed there is no training matrix | Training matrix should be developed and updated as at when due | RAY integrated service | Closed | 2022 Training Matrix sighted
| 08.07.2021 |  | TECQHSE/EXT/AUD.R/02/2021 | Observed there is no roof in the pipe shortage area | Roof should be made available for pipe since buggying can only be achieved on a favourable weather | RAY integrated service | Closed | Aluminium Roof constructed
8TH JUNE 2021 | 07.07.2021 | RAY integrated services ltd | TECQHSE/EXT/AUD.R/02/2021 | Observed there is no safe haven at the RAY integrated services Ltd | A save haven should be provided for personnel safety in the event of security threat | RAY integrated service | Open
2021-03-23 | 22/4/2021 | D AND CLEASING PLC. | TECQHSE/EXT/AUD.R/01/2021 | Observed some vehicles with expired fire extinguishers, first aid box with expired contents. | Critical safety equipment and materials must be available in all vehicles and in the facility. | C & I Leasing PLC | Closed | ER Equipments placed in vehicles
| 22/4/2021 |  | TECQHSE/EXT/AUD.R/01/2021 | Quarterly drills not held since October, 2019 – (report of the emergency drill conducted 3rd October, 2019. | Emergencies occurs irrespective of pandemics hence, modified drills should be considered and should include road traffic drills | C & I Leasing PLC | Open
| 22/4/2021 |  | TECQHSE/EXT/AUD.R/01/2021 | Absence of documented evidence describing controls or restrictions for night transportation. | Night journeys should be discouraged. However, duly authorized waivers should be prepared for unavoidable night movements. | C Leasing PLC | Open
| 2021-03-23 |  | TECQHSE/EXT/AUD.R/01/2021 | NCDC Required Covid-19 protocols (temperature checks, hand washing, social distancing) not observed on entry into the premises. | Immediate implementation of all NCDC COVID 19_ directives for business establishments | C -Managing Director | Closed | Directives visible within the premises
20/03/2019 | 30/5/2019 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | Company Vehicle insurance was provided but the workman compensation insurance were not sighted at the time of the audit | Provide workman compensation insurance for all | H MD | Closed | Recommendation implemented
20/03/2019 | 2019-01-04 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | TBT are observed but recent records were not available during the audit | Redesign TBT template to include controls and attendee signatories and document for all hazardous activities. | H MD | Closed | Recommendation implemented
20/03/2019 | ON GOING | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | Driver incentive cash rewards are issued but no typical evidence is documemted | Personnel appraisal should be carried out at least once in two years including awards | H MD | Closed | Recommendation implemented
20/03/2019 | 2019-01-04 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | No night journey waiver form is in place for HOPESON team , however journeys are timed not to spill into night trips | Night driving should be discouraged to ALARP. Review night journey hours to 6:00Pm and proffer solutions for contingencies | H MD | Closed | Recommendation implemented
20/03/2019 | 2019-03-05 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | Most past audits non conformities have been closed out but some few ones are yet to completely closed out | Modify tracker to identify all scheduled audits, inspection and other actions and follow up to ensure all actions are done or closed out. Keep records off all audit and inspection reports. | SWDA | Closed | Recommendation implemented
20/03/2019 | 31/3/2019 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | Company have appraised and promoted several drivers assistance to full Drivers but not documented appraisal form is in place | Documentation sysetm to be updated | H MD | Closed | Recommendation implemented
20/03/2019 | 30/3/2019 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | The Emergency plans were not stand alone documents displayed on notice board for all to access, they were shown form HSE Manual | Develop and emergency planand attach the emergency response competent personnel. This should be pasted in all notice boards and sent across all department | H MD | Closed | Recommendation implemented
20/03/2019 | 31/3/2019 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | Drivers interviewed are not conversant with their resposibilties or know their roles & procedures during fire or security breach situation | In- housing training to be carried out often | H MD | Closed | Recommendation implemented
20/03/2019 | 30/3/2019 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | Emergency phone numbers are not displayed and inserted in their phones only the MD is called to make cruisial emergency calls | All emergency respond contacts should be pasted on each vehicle for easily access in case of any emergency | SWDA HSE | Closed | Recommendation implemented
20/03/2019 | 2019-01-04 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | No evidence of a typical journey drill have been carried out so far was shown to us | Emergencies occurs irrespective of pandemics hence, modified drills should be considered and should include road traffic drills | H HSE | Closed | Recommendation implemented
20/03/2019 | 31/3/2019 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | There is a preventive maintenance schedule but it is not a roboust spread sheet that is automated to shown due maintenance time | An automated preventive maintenace tracker for quick reminder to be developed | H HSE | Closed | Recommendation implemented
20/03/2019 | 2019-01-04 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | faults are tracked in a note book are not updated as last record was since December 2018 | Tracker update should be carried out frequent | H HSE | Closed | Recommendation implemented
20/03/2019 | 31/3/2019 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | The vehicle parking Area is quite spacious and suitable but no segregational floor marking and appriopraite safety signages | Visible segregation mark on personnel path way with safety signages to be provided | H HSE | Closed | Recommendation implemented
20/03/2019 | 27/03/2019 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | We observed an expired fire extinguisher in a typical truck inspected | Critical safety equipment and materials must be available in all vehicles and in the facility. | H HSE | Closed | Recommendation implemented
20/03/2019 | 27/03/2010 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | First box was found but not fully kitted | Critical safety equipment and materials must be available in all vehicles and in the facility. | SWDA HSE | Closed | Recommendation implemented
20/03/2019 | 31/03/2019 | H HAULAGE NIG.LTD | HSE/AUD/0/2019 | Reflective vest was not seen and flash light was available but not working | As stated in findings | H HSE | Closed | Recommendation implemented
2018-08-07 | Decc,2018 | Facility | HSE/AUD/01/18 | Occupational health and safety performance is not formally reviewed by top management and HSEMS review minutes are not available | Review HSE performance and management system at periodic intervals | MD | Closed | Recommendation implemented
2018-08-07 | Decc,2018 | G Facility | HSE/AUD/01/18 | Occupational health and safety performance is not formally reviewed by top management and HSEMS review minutes are not available | Review HSE performance and management system at periodic intervals | MD | Closed | Recommendation implemented
2018-08-07 | Oct 2,2018 | G Facility | HSE/AUD/01/18 | Poor documentation control with lack of approvals, review, retention period on a significant number of document | Documents should be approved prior to issuance and reviewed at periodic intervals to reflect changes and continual | MD | Closed | Recommendation implemented
2018-08-07 | 2018-08-01 | GFacility | HSE/AUD/01/18 | First aid cases are not investigated | All accidents must be reported, investigated and learning's shared with staff | MD | Closed | Recommendation implemented
2018-08-07 | Oct 2,2018 | Facility | HSE/AUD/01/18 | Absence of supplier assessment and or audits since 2014 | Grocery suppliers must be audited and or inspected to verify product conformance and elimination of health risk. | MD | Closed | Recommendation implemented
2018-08-07 | 2018-08-01 | GFacility | HSE/AUD/01/18 | Poor staff attendance at monthly safety meeting | Develop strategy for ensuring participation in safety programs | MD | Closed | Recommendation implemented
2018-08-07 | 2018-08-01 | GFacility | HSE/AUD/01/18 | Caterers are issued employment before fitness to work is determined | Conduct pre-employ medical screening before staff placement. | MD | Closed | Recommendation implemented
2018-08-07 | 2018-08-01 | GFacility | HSE/AUD/01/18 | Cliented complaints are domiciled at the rig sites and may not be communicated to the base office | Develop means of accessing gall issues from clients, track and follow up open actions till closure | MD | Closed | Recommendation implemented
2018-08-01 | Aug 22,2018 | SCO | HSE/AUD/01/18 | HSE MS document was seen but the revision page was not signed by the reviewed action parties | A review should be made with parties sign and dating the document | MD | Closed | Recommendation implemented
2018-08-01 | Sept.2.2018 | SCO | HSE/AUD/01/18 | No critical HSE responsibility of staff was clearly defined and duly signed by staff | critical HSE responsibility for duly signed by staff should be clearly defined at the base | MD | Closed | Recommendation implemented
2018-08-01 | Aug 16,2018 | SCO | HSE/AUD/01/18 | Training program and matrix was not shown only attendance list of various trainings was shown without any evidence training | More robust training matrix, training plans as well as training records of personnel need to be available | MD | Closed | Recommendation implemented
2018-08-01 | Aug 15,2018 | SCO | HSE/AUD/01/18 | No hazard identificafication technique used here as TRICs cards are not used by the HSE Team only generic HEMP & JSA are in place | A definite hazard identificafication technique should be in place for the staff to identify the risks associated with their jobs | MD | Closed | Recommendation implemented
2018-08-01 | Sept.2,2018 | SCO | HSE/AUD/01/18 | No periodic Risk assessment tracker for analysising risks in place | A action risk assessment tracker and remedial corrective measure should be put in place | MD | Closed | Recommendation implemented
2018-08-01 | Aug 16,2018 | SCO | HSE/AUD/01/18 | No Management of change (MOC) procedure document is in place yet only ablank control form was shown | A sign management of change procedure document is and precaution is recommended. | MD | Closed | Recommendation implemented
2018-08-01 | Aug 16,2018 | SCO | HSE/AUD/01/18 | Work procedures are not available and are not implemented duly at the worksite | Work or task procedure are to be made available as part of PTW requirement for all non-routine tasks | MD | Closed | Recommendation implemented
2018-08-01 | Aug 18,2018 | SCO | HSE/AUD/01/18 | Incidents are reported, investigated but there are no action tracker to monitor the corrective actions and LFIs are not tracked in your reports | An incidents record tracker with action closeout date is recommended | MD | Closed | Recommendation implemented
2018-08-01 | Sept 2,2018 | SCO | HSE/AUD/01/18 | No annual audit plan was shown | No annual audit schedule or program was shown | MD | Closed | Recommendation implemented
2018-08-01 | Sept 9,2018 | SCO | HSE/AUD/01/18 | No evidence of Management Review Report to verify the effective of the system | Management System Review Report evidence on audit follow up and close out should be made available | MD | Closed | Recommendation implemented
2018-08-01 | Sept 9,2018 | SCO | HSE/AUD/01/18 | No corrective acts procedure of customers complaints was shown | A coorective procedure for product or service is available on demand by the customer | MD | Closed | Recommendation implemented
2018-08-01 | Aug 24,2018 | SCO | HSE/AUD/01/18 | Apart from FTW, a system of random/spot testing should be developed for alcohol, BP etc | There is the need to introduce random medical fitness test on staff periodiically | MD | Closed | Recommendation implemented
2018-08-01 | Sept 22,2018 | SCO | HSE/AUD/01/18 | Emergency exits are not visibly identified | Informative signs should be placed at all exits and emergency exits, staircase, work area etc. | MD | Closed | Recommendation implemented
June 2. 2017 | Jun 30,2017 | Gensis Facility | HSE/AUD/01/17 | Provision of backup burners. | G provided a new fit for purpose bratt pan | Supervisor | Closed | Recommendation implemented
June 2. 2017 | Jun 30,2017 | Gensis Facility | HSE/AUD/01/17 | G personnel for NBDC Rig 101 to be certified for FTW and Food handling | Most of G personnel for the NBDC Rig 101 operation are duely certified for food handling. The remaining few personnel will be certified two daysprior to mobilization for FTW and Food handling. | Supervisor | Closed | Recommendation implemented
June 2. 2017 | July 30,2017 | Gensis Facility | HSE/AUD/01/17 | G is yet to train the minimum number of personnel required for the NBDC Rig 101 operation. | We only sighted certificates for 2 personnel, the remaining are to proceed on training by 06-06-17 | Supervisor | Closed | Recommendation implemented
June 2. 2017 | Jun 30,2017 | Gensis Facility | HSE/AUD/01/17 | Management c Inspection for G | G management representatives made a commitment to carry out Management c Inspection at least once every two months in the course of the Rig 101 operation. | Supervisor | Closed | Recommendation implemented
June 2. 2017 | Jun 30,2017 | Gensis Facility | HSE/AUD/01/17 | G does not have a spare bain-marie for the Rig 101 operation | NBDC to provide one | swda | Closed | Recommendation implemented
June 2. 2017 | Jun 30,2017 |  | HSE/AUD/01/17 | Helicopter underwater Escape Training for G Personnel | All G personnel for the Rig 101 operation are HUET certified | Supervisor | Closed | Recommendation implemented
July 9. 2015 | August.17.2015 | RAY integrated services ltd | HSE/AUD/02/2015 | No existence process in place for analysing new risk task in case of deviation | Develop process for creating deviations that may introduce new risk to task execution and cascade procedures across departments | Managing Director | Closed | Recommendation implemented
July 9. 2015 | September.22.2015 | RAY integrated services ltd | HSE/AUD/02/2015 | No daily statistics electronically in place | Update and record daily statistics electronically and measure against set targets. Schedule meetings for HSE performance reviews | MD /HSE Manager | Closed | Recommendation implemented
July 9. 2015 | Immediate | RAY integrated services ltd | HSE/AUD/02/2015 | JSA not properly developed | Redesign JSA template to include controls and attendee signatories and document for all hazardous activities. | HSE Officer | Closed | Recommendation implemented
July 9. 2015 | August.17.2015 | RAY integrated services ltd | HSE/AUD/02/2015 | No tracker in place for audits , inspection and follow up to closure | Modify tracker to identify all scheduled audits, inspection and other actions and follow up to ensure all actions are done or closed out. Keep records off all audit and inspection reports. | HSE Manager | Closed | Recommendation implemented
July 9. 2015 | August.24.2015 | RAY integrated services ltd | HSE/AUD/02/2015 | Night journey must be avoided if necessary | Night driving should be discouraged to ALARP. Review night journey hours to 6:00Pm and proffer solutions for contingencies | Managing Director | Closed | Recommendation implemented
July 9. 2015 | September.22.2015 | RAY integrated services ltd | HSE/AUD/02/2015 | Insufficient stop cards reporting by personnel | Stop cards should be used at the base and c to record all anomalies and safety culture promoted and enhanced by recognizing deserving staff. | HSE Officer | Closed | Recommendation implemented
July 9. 2015 | August.24.2015 | RAY integrated services ltd | HSE/AUD/02/2015 | No existence SHOC for all hazardous chemicals | Develop SHOC for all hazardous chemicals and communicate to handlers and/or place SHOC cards at strategic point s of use. | HSE Officer | Closed | Recommendation implemented
July 9. 2015 | August.24.2015 | RAY integrated services ltd | HSE/AUD/02/2015 | Observed waste bins are not color coded | Use color coded bins to segregate harzardous/non hazardous waste etc. Also, ensure licensed vendor disposes waste at approved dumpsite. | HSE Manager | Closed | Recommendation implemented
July 9. 2015 | August.24.2015 | RAY integrated services ltd | HSE/AUD/02/2015 | No list for all the items in the first aid kit | Insert List of all contents in the first aid box including products expiration date and check periodically | HSE Officer | Closed | Recommendation implemented
July 9. 2015 | Henceforth | RAY integrated services ltd | HSE/AUD/02/2015 | No evidence of staff assessment and training documented | All Trainings regarding work task should be documented and staff assessment should be done. | HSE Manager | Closed | Recommendation implemented
July 9. 2015 | August.24.2015 | RAY integrated services ltd | HSE/AUD/02/2015 | No drill schedule plan available | A Drill schedule should be developed and followed | HSE Manager | Closed | Recommendation implemented
July 9. 2015 | September.22.2015 | RAY integrated services ltd | HSE/AUD/02/2015 | No informatives signages place at the strategic places | Informative signs should be placed at all exits and emergency exits, staircase, work area etc. | HSE Officer | Closed | Recommendation implemented
July 9. 2015 | August.24.2015 | RAY integrated services ltd | HSE/AUD/02/2015 | No inspection and service schedule for firefighting equipments | Develop inspection and service schedule for firefighting equipments and ensure maintenance dates are pasted on cylinders. | HSE Manager | Closed | Recommendation implemented
July 9. 2015 | August.24.2015 | RAY integrated services ltd | HSE/AUD/02/2015 | Maintenance and servicing plan was not seen | Develop and implement plan for preventive maintenance and servicing of equipment. | HOD | Closed | Recommendation implemented